Capstone Project Report

Report 2 – Project Management Plan

– Ho Chi Minh, February 2025 –

Table of Contents

I. Record of Changes	3

II. Project Management Plan	4

1. Overview	4

1.1 Scope & Estimation	4

1.2 Project Objectives	5

1.3 Project Risks	5

2. Management Approach	6

2.1 Project Process	6

2.2 Quality Management	7

2.3 Training Plan	7

3. Project Deliverables	7

4. Responsibility Assignments	8

5. Project Communications	8

6. Configuration Management	9

6.1 Document Management	9

6.2 Source Code Management	9

6.3 Tools & Infrastructures	9

# I. Record of Changes

| Date | A* M, D | In charge | Change Description |
| --- | --- | --- | --- |
| 10/02/2025 | A | Nam | Add Configuration Management |
| 10/02/2025 | A | Nam | Add Project Communications |
| 10/02/2025 | A | An | Add Responsibility Assignments |
| 30/04/2025 | A | Luân | Add from final report |

*A - Added M - Modified D - Deleted

# II. Project Management Plan

## 1. Overview

### 1.1 Scope & Estimation

| # | WBS Item | Complexity | Est. Effort (man-days) |
| --- | --- | --- | --- |
| 1 | Initiating |  |  |
| 1.1 | Collect requirement | Medium | 14 |
| 2 | Planning |  |  |
| 2.1 | Create plan document | Complex | 10 |
| 3 | Executing |  |  |
| 3.1 | Analysis |  |  |
| 3.1.1 | Analysis requirement | Complex | 12 |
| 3.2 | Design and prototyping |  |  |
| 3.2.1 | Design customer web/mobile application | Complex | 20 |
| 3.2.2 | Design customer web/mobile application | Complex | 20 |
| 3.2.3 | Design platform’s staff web application | Complex | 15 |
| 3.3 | Implementation |  |  |
| 3.3.1 | Implement base feature |  |  |
| 3.3.1.1 | Login and logout | Simple | 2 |
| 3.3.1.2 | Update profile | Simple | 2 |
| 3.3.1.3 | Register | Simple | 2 |
| 3.3.1.4 | Change and reset password | Simple | 2 |
| 3.3.2 | Implement woodworker feature |  |  |
| 3.3.2.1 | Manage service | Medium | 4 |
| 3.3.2.2 | Manage product | Medium | 2 |
| 3.3.2.3 | Manage design idea | Complex | 8 |
| 3.3.2.4 | Manage post | Medium | 2 |
| 3.3.2.5 | Manage service order | Complex | 20 |
| 3.3.2.6 | Manage guarantee order | Complex | 20 |
| 3.3.2.7 | Manage wallet | Medium | 10 |
| 3.3.2.8 | Manage customer complaint | Medium | 5 |
| 3.3.2.9 | Manage review | Medium | 2 |
| 3.3.3 | Implement customer feature |  |  |
| 3.3.3.1 | Search, filter, view list/detail woodworker | Medium | 3 |
| 3.3.3.2 | Search, filter, view list/detail product | Medium | 3 |
| 3.3.3.3 | Search, filter, view list/detail design idea | Medium | 3 |
| 3.3.3.4 | Book and manage customization service | Complex | 15 |
| 3.3.3.5 | Book and manage personalization service | Complex | 15 |
| 3.3.3.6 | Review and rating order | Medium | 2 |
| 3.3.3.7 | Manage wallet | Medium | 10 |
| 3.3.3.8 | Manage complaint | Medium | 10 |
| 3.3.4 | Implement moderator feature |  |  |
| 3.3.4.1 | Manage woodworker performance | Medium | 6 |
| 3.3.4.2 | Send performance email | Medium | 3 |
| 3.3.5 | Implement staff feature |  |  |
| 3.3.5.1 | Manage customer’s review | Medium | 3 |
| 3.3.5.2 | Mange woodworker’s response | Medium | 3 |
| 3.3.5.3 | Manage complaint | Complex | 10 |
| 3.3.6 | Implement admin feature |  |  |
| 3.3.6.1 | Manage woodworker registration | Medium | 10 |
| 3.3.6.2 | Manage configuration | Medium | 10 |
| 3.4 | Testing |  |  |
| 3.4.1 | Unit testing | Complex | 12 |
| 3.4.2 | Integration test | Complex | 12 |
| 3.4.3 | System test | Complex | 12 |
| 4 | Monitoring and controlling |  |  |
| 4.1 | Control the process | Complex | 12 |
| 4.2 | Track performance and quality | Complex | 12 |
| 5 | Closing |  |  |
| 5.1 | Report | Simple | 20 |
| Total Estimated Effort (man-days) |  |  | 358 |

### 1.2 Project Objectives

| # | Testing Stage | No. of Defects | % of Defect | Notes |
| --- | --- | --- | --- | --- |
| 1 | Reviewing | 20 | 27,6% |  |
| 2 | System Test | 40 | 72,4% |  |
| 3 | User Acceptance Test | X | X |  |
| Total |  | 60 | 100% |  |

### 1.3 Project Risks

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | Technology risk: cannot find the suitable solution for technique problems, the software cannot fulfil the expectation. | High | Medium | Do more research on official resources, discuss with mentor. |
| 2 | Requirement changes: requirements unexpected Changes. | Critical | Medium | Chose another way of solution to respond to those changes. |

## 2. Management Approach

### 2.1 Project Process

References: What is Scrum? | The Agile Journey: A Scrum overview

Our project, adopted the Scrum model, an Agile framework for software development, for the following reasons:

- We worked with a small team of 4 members, making it unnecessary to follow every stage of a traditional methodology like Waterfall. Instead, Scrum allowed us to iterate quickly and focus on delivering value continuously.

- By organizing work into short sprints, we were able to easily analyze the next priorities and refactor whenever necessary, ensuring flexibility throughout the development cycle.

- The limited time frame of each sprint created a healthy pressure, motivating the team to complete tasks efficiently and maintain momentum across the project.

Product backlog

### 2.2 Quality Management

To maintain code and project quality:

- Conduct regular code reviews.

- Enforce consistent coding standards.

- Feedback loop: Demos and user feedback sessions every sprint.

### 2.3 Training Plan

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| Git & GitHub Workflow | All Members | Week 1 only | Mandatory |
| Jira + Agile Practice | All Members | Week 1 only | Mandatory |
| ReactJS Essentials | Võ Trọng Luân | Week 1 – Week 2 | Mandatory |
| React Native Basics | Võ Trọng Luân Lê Nguyên An Nguyễn Đặng Phương | Week 1 – Week 2 | Mandatory |
| Spring Boot Core | Trần Việt Phúc Nguyễn Đặng Phương Nam | Week 1 – Week 2 | Mandatory |

## 3. Project Deliverables

| # | Deliverable | Due Date | Notes |
| --- | --- | --- | --- |
| 1 | User Requirements Document (URD) | 22/02/2025 | Defines user needs and expectations. |
| 2 | Software Requirements Specification (SRS) | 22/02/2025 | Outlines detailed functional and non-functional requirements. |
| 3 | System Architecture Design | 22/02/2025 | Includes high-level system design, database schema, and component interactions. |
| 4 | Web Application | 05/04/2025 | A web-based platform for guests, customers, woodworkers, and administrators with full functionality for booking services, reviews, account management, etc. |
| 5 | Mobile Application | 05/04/2025 | A user-friendly mobile app optimized for seamless user experience with features like the web application. |
| 6 | Backend System (RESTful API) | 05/04/2025 | Backend system ensuring authentication, service management, chat support, cost calculations, and payment integration. |
| 7 | Database System | 22/02/2025 | Data management system using MySQL/SQL Server with key tables such as Users, Bookings, Services, Payments, Reviews, etc. |
| 8 | Deployment & Hosting Deliverables | 05/04/2025 | Includes source code, server configuration, and deployment documentation on Railway. |
| 9 | Final Report & Presentation | 28/04/2025 | A final report summarizing the development process, achieved results, challenges faced, along with a presentation and product demo video |

## 4. Responsibility Assignments

D~Do; R~Review; S~Support; I~Informed; <blank>- Omitted

| Responsibility | luanvtse171436 | phuctvse171429 | anlnse171475 | namndpse171442 |
| --- | --- | --- | --- | --- |
| Project Planning & Tracking | D | D | D | D |
| Prepare Project Introduction Document | D | D | D | D |
| Prepare SRS Document (Overview Part) | D | D | D | D |
| Prepare SRS Document (User Requirements) | D | D | D | D |
| Develop System Architecture | D | D | D | D |
| Implement Backend Components | R | D | R | D |
| Implement Frontend Components | D | R | R | R |
| Implement App Components | S | R | D | S |

## 5. Project Communications

| Communication Item | Who/ Target | Purpose | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Texting | Supervisor + Team member | • Confirm Meeting time • Report Working progress • Internal conversations | Usually | Zalo |
| Meeting offline | Supervisor + Team member | • Progress report • Report and handle problem • Review task | Weekly |  |
| Tracking progress | Team member | • Check personal tasks • Tracking progress of project on Jira | Daily | Jira |

## 6. Configuration Management

### 6.1 Document Management

- Use OneDrive to save document and for real-time editing on Microsoft Word.

- Use Google Drive to save meeting report, meeting record, diagram, image, design, document to each category folder

### 6.2 Source Code Management

- GitHub server to store source code.

- Follow the rule of team when using Git:

  - Commit and note the changes details often.

  - Review carefully before push into develop branch.

  - Fetch, review and resolve conflicts when merging usually

### 6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | React (Web), React Native (Mobile), Spring Boot (Back-end) |
| Database | MySQL |
| IDEs/Editors | Visual Studio Code, IntelliJ |
| Diagramming | Visual Paradigm, DrawIO, Mermaid Chart |
| Documentation | Ms Office, Google Docs/Sheets/Slides |
| Version Control | GitHub (Source Codes), Google Drive (Documents) |
| Deployment server | Railway, Vercel |
| Project management | Jira (Schedule), GitHub (Tasks, Defects) |