## General Task
Id | Task | Short Description | In Charge | Status
1 |  | Create data file to insert data into database | All | In Progress
2 |  | Login, Register, Refresh Token, Logout, Forget Password, Change Password, Verify email, Verify phone number | Quang | Testing
3 |  | Staff are able to CRUD service list, Include Filter, Search | Phúc | In Progress
4 |  | Update profile, Get Userlist (Include Filter), Search user | Quang | In Progress
5 |  | Customer can CRUD their pet list | Luân | Done
6 |  | Customer can book appoinment, check & choose pet, choose doctor, system auto choose doctor, staff can book appointment for customer | Luân | Testing
7 |  | Staff can manage Service include Create, Update, Delete, View all | Phúc | In Progress
8 |  | Staff can manage Cage include Create, Update, Delete, view all | Phúc | In Progress
9 |  | Staff can manage Vet incldue Create, Delete, View all | Phúc | In Progress
13 |  | Customer create transaction + pay online, Staff create transaction and confirm payment | Quang | Testing
14 |  | Include write for fet, view for user | Luân | Not Yet
15 |  | Include write for fet, view for user | Phúc | Not Yet

## API
Id | Function | Short Description | API-link (include parameter) | Method | Authentication | Parameters | Request body | In charge | Status
0 | Example Function | Hàm này trả về các thông tin của một lớp theo classId, query theo string bên kia | http://localhost:7189/api/classes/{classId} | GET | JWT | pageSize pageNumber classId |  | Luân | Done
1 | Login | Hàm trả về 200 UserLoginResponseDto {fullname, jwt(emal,sdt,username), refreshtoken}, 204, 400, Người dùng không được đăng nhập khi chưa verify | /user/authenticate | POST | None |  | LoginDto {phone number, password} | Quang | Done
2 | Logout | Hàm trả về 200, 204, 400 Inactive JWT và RefreshToken | /user/logout | POST | JWT |  | RefreshToken | Luân | Not yet
3 | Send OTP | Hàm trả về 201(gửi mã OTP 6 số về số điện thoại), 400 | /user/send-otp | POST | JWT |  | RefreshToken, UserId | Quang | Not yet
4 | Verify phone number | Hàm trả về 200, 400 client nhập mã qua API để verify | /user/verify-phone-number | POST | JWT |  | RefreshToken, Phonenumber, OTP |  | Not yet
5 | Register | Hàm trả về 201, 400, 409(id, email, sdt), mã hóa password định dạng SHA-256 + mã 6 số ngẫu nhiên | /user/register | POST | None, Customer |  | CustomerRequestDto | Quang | Done
6 | Forget Password | Hàm mã hóa password định dạng SHA-256 + mã 6 số ngẫu nhiên, update password, trả về 200, 400 | /user/change-forgot-password | POST | None |  | RefreshToken, Phonenumber, OTP, NewPassword
7 | Change Password | Hàm mã hóa password định dạng SHA-256 + mã 6 số ngẫu nhiên, update password, trả về 200, 400 | /user/change-password | POST | None |  | RefreshToken, Phonenumber, OTP, OldPassword, NewPassword
8 | Get user | Hàm trả về thông tin 200 UserResponseDto, 204, 400,403 | user/{id} | GET | JWT | UserId | UserId
9 | Get user list | Hàm trả về 200 List<UserResponseDto>, 204, 400,403 | user/list | GET | JWT | pageSize pageNumber
10 | Create User | Hàm trả về 201(UserResponseDto{username, fullname, email, sdt}), 400, 403, 409, mã hóa password định dạng SHA-256 + mã 6 số ngẫu nhiên | user/create | POST | JWT, Staff |  | UserRequestDto
12 | Update profile | Hàm trả về 200, 400 | user/update/{id} | PUT | JWT |  | UserUpdateDto
13 | Delete user | Hàm trả về 200, 400, 403, update delete by & time | user/delete/{id} | DELETE | JWT, Staff
| Add Vet | 201 | user/vet/add | POST | JWT Staff
| Get Vet list | 200 | user/vet/list | GET | JWT Staff
| Add pet | 201 | pet/add | POST | JWT Cus
| Get pet list | 200 | pet/list | GET | JWT
| Add service | 201 | service/add | POST | JWT Staff
| Get all service | 200 |  | GET | JWT
update pet
delete pet
| Get all transaction | 200, 404, 400 |  | GET | JWT |  |  | Quang | Done
| get transaction by id | 200, 404, 400 |  | GET | JWT |  |  | Quang | Done
| get customer transaction | 200, 404, 400 |  | GET | JWT, Customer |  |  | Quang | Done
| create transaction | 200, 404, 400 |  | POST | JWT, Customer, Staff |  |  | Quang | Done
| update payment | 200, 404, 400 |  | PUT | JWT, Staff |  |  | Quang | Done