## Report
Link report mẫu | https://drive.google.com/file/d/1GSCOXZJndBDxocNCQGiFJKY41jiqW68H/view?usp=drive_link
Id | Description | Note | In charge | Status
1 | II - 1. Prodcut Overview |  | Phong | Done
2 | II - 2. User Requirements | Bỏ use case description vào đây để t tự move qua | Phúc | Done
3 | II - 3.1.1 Functional Requirements |  | Anh
4 | II - 3.1.2 Screen Authorization |  | Luân | Done
5 | II - 3.2 Entity Relationship Diagram |  | Phong | Done
6 | II - 4. Non-Functional Requirements |  | Nam | Done
7 | II - 5.1 Business Rules | Dời Business Rule từ use case description xuống đây đánh số | All
8 | II - 5.2 Application Messages List |  | Phong | Done
9 | III - 3.1 Pet Feature |  | Luân | Done
10 | III - 3.2 Booking Feature | activity: book, cancel; sequence book | Anh
11 | III - 3.3 Medical Record Feature | activity: vet write, user view; sequence: vet write | Phúc | In Progress
12 | III - 3.4 Hospitalization Feature | activity: vet write, user view; sequence: vet write | Quang
13 | III - 1.1 System Architecture | Vẽ như report mẫu =))) | All
14 | III - 2. Database Design | Xem report mẫu làm =)) | Quang
15 | III - 3.5.1 Register Activity Diagram, 3.5.2 Login Activity Diagram |  | Nam | Done
16 | Fix error =)) |  | Luân | Done

## Sheet3
Entity Name | Attributes | Description | Domain | Null | No | Table | Description
Appointment | Id {PK} | Unique identifier | int | No | 1 | Appointment | Table storing appointment details
| TimeTableId | Foreign key, Identifier for timetable | int | No | 2 | AppointmentPets | Table linking appointments to pets
| Note | Appointment note | nvarchar(max) | Yes | 3 | AppointmentService | Table linking appointments to services
| Status | Status of the appointment | int | No | 4 | Cage | Table storing cage details
| BookingType | Type of booking | int | No | 5 | Configurations | Table storing configuration settings
| Rating | Appointment rating | smallint | Yes | 6 | Hospitalization | Table storing hospitalization records
| Feedback | Feedback from appointment | nvarchar(max) | Yes | 7 | MedicalItem | Table storing medical items
| CreatedBy | User who created the record | int | Yes | 8 | MedicalItemMedicalRecord | Table linking medical items to records
| LastUpdatedBy | User who last updated the record | int | Yes | 9 | MedicalRecord | Table storing medical records
| DeletedBy | User who deleted the record | int | Yes | 10 | Pet | Table storing pet details
| CreatedTime | Record creation time | datetimeoffset(7) | No | 11 | RefreshTokens | Table storing refresh tokens
| LastUpdatedTime | Last update time | datetimeoffset(7) | No | 12 | Roles | Table storing roles
| DeletedTime | Record deletion time | datetimeoffset(7) | Yes | 13 | Service | Table storing services
| VetId | Foreign key, Veterinarian ID | int | No | 14 | TimeTable | Table storing timetable details
| AppointmentDate | Date of appointment | date | No | 15 | Transaction | Table storing transactions
AppointmentPets | Id {PK} | Unique identifier | int | No
| AppointmentId | Foreign key, Identifier for appointment | int | No | 16 | TransactionDetails | Table storing transaction details
| PetId | Foreign key, Identifier for pet | int | No | 17 | UserRoles | Table linking users to roles
AppointmentService | Id {PK} | Unique identifier | int | No
| AppointmentsId | Foreign key, Identifier for appointment | int | No | 18 | Users | Table storing user details
| ServicesId | Foreign key, Identifier for service | int | No
Cage | Id {PK} | Unique identifier | int | No
| Capacity | Capacity of the cage | int | No
| Material | Material of the cage | nvarchar(max) | Yes
| Room | Room identifier | int | Yes
| Address | Address of the cage | nvarchar(max) | Yes
| Description | Description of the cage | nvarchar(max) | Yes
| Note | Note about the cage | nvarchar(max) | Yes
| CreatedBy | User who created the record | int | Yes
| LastUpdatedBy | User who last updated the record | int | Yes
| DeletedBy | User who deleted the record | int | Yes
| CreatedTime | Record creation time | datetimeoffset(7) | No
| LastUpdatedTime | Last update time | datetimeoffset(7) | No
| DeletedTime | Record deletion time | datetimeoffset(7) | Yes
| IsAvailable | Availability status | bit | No
Configurations | Id {PK} | Unique identifier | int | No
| ConfigKey | Configuration key | nvarchar(max) | No
| Value | Configuration value | nvarchar(max) | No
| CreatedBy | User who created the record | int | Yes
| LastUpdatedBy | User who last updated the record | int | Yes
| DeletedBy | User who deleted the record | int | Yes
| CreatedTime | Record creation time | datetimeoffset(7) | No
| LastUpdatedTime | Last update time | datetimeoffset(7) | No
| DeletedTime | Record deletion time | datetimeoffset(7) | Yes
Hospitalization | Id {PK} | Unique identifier | int | No
| MedicalRecordId | Foreign key, Identifier for medical record | int | No
| CageId | Foreign key, Identifier for cage | int | No
| TimeTableId | Foreign key, Identifier for timetable | int | Yes
| Date | Hospitalization date | date | No
| HospitalizationDateStatus | Status of the hospitalization date | int | No
| Reason | Reason for hospitalization | nvarchar(max) | Yes
| Diagnosis | Diagnosis information | nvarchar(max) | Yes
| Treatment | Treatment information | nvarchar(max) | Yes
| Note | Note about the hospitalization | nvarchar(max) | Yes
| CreatedBy | User who created the record | int | Yes
| LastUpdatedBy | User who last updated the record | int | Yes
| DeletedBy | User who deleted the record | int | Yes
| CreatedTime | Record creation time | datetimeoffset(7) | No
| LastUpdatedTime | Last update time | datetimeoffset(7) | No
| DeletedTime | Record deletion time | datetimeoffset(7) | Yes
| VetId | Foreign key, Veterinarian ID | int | No
MedicalItem | Id {PK} | Unique identifier | int | No
| Name | Name of the medical item | nvarchar(max) | No
| Description | Description of the medical item | nvarchar(max) | Yes
| Price | Price of the medical item | decimal(18, 0) | No
| Quantity | Quantity of the medical item | int | No
| CreatedBy | User who created the record | int | Yes
| LastUpdatedBy | User who last updated the record | int | Yes
| DeletedBy | User who deleted the record | int | Yes
| CreatedTime | Record creation time | datetimeoffset(7) | No
| LastUpdatedTime | Last update time | datetimeoffset(7) | No
| DeletedTime | Record deletion time | datetimeoffset(7) | Yes
| MedicalItemType | Type of the medical item | int | No
| Note | Note about the medical item | nvarchar(max) | Yes
MedicalItemMedicalRecord | Id {PK} | Unique identifier | int | No
| MedicalItemsId | Foreign key, Identifier for medical item | int | No
| MedicalRecordsId | Foreign key, Identifier for medical record | int | No
MedicalRecord | Id {PK} | Unique identifier | int | No
| PetId | Foreign key, Identifier for pet | int | No
| RecordDetails | Details of the record | nvarchar(max) | Yes
| Date | Date of the record | datetimeoffset(7) | No
| Diagnosis | Diagnosis information | nvarchar(max) | Yes
| Treatment | Treatment information | nvarchar(max) | Yes
| Note | Note about the record | nvarchar(max) | Yes
| NextAppointment | Next appointment date and time | datetimeoffset(7) | Yes
| PetWeight | Weight of the pet | decimal(5, 2) | No
| ServiceId | Foreign key, Identifier for service | int | Yes
| UserEntityId | Foreign key, Identifier for user entity | int | Yes
| CreatedBy | User who created the record | int | Yes
| LastUpdatedBy | User who last updated the record | int | Yes
| DeletedBy | User who deleted the record | int | Yes
| CreatedTime | Record creation time | datetimeoffset(7) | No
| LastUpdatedTime | Last update time | datetimeoffset(7) | No
| DeletedTime | Record deletion time | datetimeoffset(7) | Yes
| AddmissionDate | Admission date of the pet | datetimeoffset(7) | Yes
| DischargeDate | Discharge date of the pet | datetimeoffset(7) | Yes
Pet | Id {PK} | Unique identifier | int | No
| Name | Name of the pet | nvarchar(max) | Yes
| Species | Species of the pet | nvarchar(max) | Yes
| Breed | Breed of the pet | nvarchar(max) | Yes
| OwnerID | Foreign key, Identifier for customer | int | No
| CreatedBy | User who created the record | int | Yes
| LastUpdatedBy | User who last updated the record | int | Yes
| DeletedBy | User who deleted the record | int | Yes
| CreatedTime | Record creation time | datetimeoffset(7) | No
| LastUpdatedTime | Last update time | datetimeoffset(7) | No
| DeletedTime | Record deletion time | datetimeoffset(7) | Yes
| DateOfBirth | Date of birth of the pet | datetimeoffset(7) | No
| IsNeutered | Neutering status | bit | No
| Gender | Gender of the pet | nvarchar(max) | Yes
RefreshTokens | Id {PK} | Unique identifier | int | No
| UserId | Foreign key, Identifier for user | int | No
| Token | Refresh token | nvarchar(max) | No
| Expires | Expiry date and time | datetimeoffset(7) | No
| CreatedBy | User who created the record | int | Yes
| LastUpdatedBy | User who last updated the record | int | Yes
| DeletedBy | User who deleted the record | int | Yes
| CreatedTime | Record creation time | datetimeoffset(7) | No
| LastUpdatedTime | Last update time | datetimeoffset(7) | No
| DeletedTime | Record deletion time | datetimeoffset(7) | Yes
Roles | Id {PK} | Unique identifier | int | No
| Name | Name of the role | nvarchar(256) | Yes
| NormalizedName | Normalized name of the role | nvarchar(256) | Yes
| ConcurrencyStamp | Concurrency stamp | nvarchar(max) | Yes
Service | Id {PK} | Unique identifier | int | No
| Name | Name of the service | nvarchar(max) | No
| Description | Description of the service | nvarchar(max) | Yes
| Duration | Duration of the service | int | No
| Price | Price of the service | decimal(18, 0) | No
| CreatedBy | User who created the record | int | Yes
| LastUpdatedBy | User who last updated the record | int | Yes
| DeletedBy | User who deleted the record | int | Yes
| CreatedTime | Record creation time | datetimeoffset(7) | No
| LastUpdatedTime | Last update time | datetimeoffset(7) | No
| DeletedTime | Record deletion time | datetimeoffset(7) | Yes
TimeTable | Id {PK} | Unique identifier | int | No
| Note | Note about the timetable | nvarchar(max) | Yes
| CreatedBy | User who created the record | int | Yes
| LastUpdatedBy | User who last updated the record | int | Yes
| DeletedBy | User who deleted the record | int | Yes
| CreatedTime | Record creation time | datetimeoffset(7) | No
| LastUpdatedTime | Last update time | datetimeoffset(7) | No
| DeletedTime | Record deletion time | datetimeoffset(7) | Yes
| EndTime | End time of the timetable | time(7) | No
| StartTime | Start time of the timetable | time(7) | No
Transaction | Id {PK} | Unique identifier | int | No
| CustomerId | Foreign key, Identifier for customer | int | No
| AppointmentId | Foreign key, Identifier for appointment | int | Yes
| MedicalRecordId | Foreign key, Identifier for medical record | int | Yes
| HospitalizationId | Foreign key, Identifier for hospitalization | int | Yes
| Total | Total amount | decimal(18, 0) | No
| PaymentDate | Payment date and time | datetimeoffset(7) | Yes
| Status | Status of the transaction | int | No
| PaymentMethod | Method of payment | int | Yes
| PaymentNote | Note about the payment | nvarchar(max) | Yes
| PaymentId | Payment identifier | nvarchar(max) | Yes
| PaymentStaffName | Name of the payment staff | nvarchar(max) | Yes
| Note | Note about the transaction | nvarchar(max) | Yes
| RefundPercentage | Percentage of refund | decimal(5, 2) | Yes
| RefundReason | Reason for refund | nvarchar(max) | Yes
| RefundDate | Refund date and time | datetimeoffset(7) | Yes
| CreatedBy | User who created the record | int | Yes
| LastUpdatedBy | User who last updated the record | int | Yes
| DeletedBy | User who deleted the record | int | Yes
| CreatedTime | Record creation time | datetimeoffset(7) | No
| LastUpdatedTime | Last update time | datetimeoffset(7) | No
| DeletedTime | Record deletion time | datetimeoffset(7) | Yes
| PaymentStaffId | Identifier for payment staff | int | Yes
| RefundPaymentId | Refund payment identifier | nvarchar(max) | Yes
TransactionDetails | Id {PK} | Unique identifier | int | No
| TransactionId | Foreign key, Identifier for transaction | int | No
| ServiceId | Foreign key, Identifier for service | int | Yes
| MedicalItemId | Foreign key, Identifier for medical item | int | Yes
| Quantity | Quantity of the item/service | int | No
| SubTotal | Subtotal amount | decimal(18, 0) | No
| Name | Name of the item/service | nvarchar(max) | Yes
| Price | Price of the item/service | decimal(18, 0) | No
UserRoles | Id {PK} | Unique identifier | int | No
| UserId | Foreign key, Identifier for user | int | No
| RoleId | Foreign key, Identifier for role | int | No
| Discriminator | Discriminator for user roles | nvarchar(21) | No
Users | Id {PK} | Unique identifier | int | No
| FullName | Full name of the user | nvarchar(max) | Yes
| Address | Address of the user | nvarchar(max) | Yes
| Avatar | Avatar image of the user | nvarchar(max) | Yes
| BirthDate | Birthdate of the user | datetimeoffset(7) | Yes
| CreatedBy | User who created the record | nvarchar(max) | Yes
| LastUpdatedBy | User who last updated the record | nvarchar(max) | Yes
| DeletedBy | User who deleted the record | nvarchar(max) | Yes
| CreatedTime | Record creation time | datetimeoffset(7) | No
| LastUpdatedTime | Last update time | datetimeoffset(7) | No
| DeletedTime | Record deletion time | datetimeoffset(7) | Yes
| Verified | Verification timestamp | datetimeoffset(7) | Yes
| OTPExpired | OTP expiration timestamp | datetimeoffset(7) | Yes
| PhoneNumberConfirmed | Confirmation status of phone number | bit | No
| UserName | Username of the user | nvarchar(256) | Yes
| NormalizedUserName | Normalized username | nvarchar(256) | Yes
| Email | Email of the user | nvarchar(256) | Yes
| NormalizedEmail | Normalized email | nvarchar(256) | Yes
| EmailConfirmed | Confirmation status of email | bit | No
| PasswordHash | Hashed password | nvarchar(max) | Yes
| ConcurrencyStamp | Concurrency stamp | nvarchar(max) | Yes
| PhoneNumber | Phone number of the user | nvarchar(max) | Yes
| TwoFactorEnabled | Two-factor authentication enabled status | bit | No
| LockoutEnd | Lockout end timestamp | datetimeoffset(7) | Yes
| LockoutEnabled | Lockout enabled status | bit | No
| AccessFailedCount | Count of failed access attempts | int | No
| OTP | OTP for user verification | nvarchar(max) | Yes

## UML task
Note: Lưu file ảnh vô Folder chung thư mục UML/Type ví dụ UML/Activy đặt tên dưới dạng Ten_Description, ví dụ: Luan_Cancel booking
Id | Type | Description | In charge | Status
1 | Activity |  | Luân
2 | Activity |  | Luân
3 | Activity |  | Luân
4 | Activity |  | Phong
5 | Activity |  | Phong
6 | Activity |  | Phong
7 | Activity |  | Phúc
8 | Activity |  | Phúc
9 | Activity |  | Phúc
10 | Activity |  | Quang
11 | Activity |  | Quang
12 | Activity |  | Quang
13 | Activity |  | Nam
14 | Activity |  | Nam
15 | Activity |  | Nam
16 | Activity |  | Anh
17 | Activity |  | Anh
18 | Activity |  | Anh
19 | Sequence |  | Luân
20 | Sequence |  | Luân
21 | Sequence |  | Phong
22 | Sequence |  | Phong
23 | Sequence |  | Phúc
24 | Sequence |  | Phúc
25 | Sequence |  | Quang
26 | Sequence |  | Quang
27 | Sequence |  | Nam
28 | Sequence |  | Nam
29 | Sequence |  | Anh
30 | Sequence |  | Anh
31 | State |  | Luân
32 | State |  | Phong
33 | State |  | Phúc
34 | State |  | Quang
35 | State |  | Nam
36 | State |  | Anh